## Workplan Steps
Phase | Activity | Task | Notes | Role (EAO / P) - Visibility | Milestone | Requirement / Dependencies | Start Date | Process | Process | Process | Logic | Metadata / Tags (Bucket association / Where does this information need to go) | Resulting Action (New Tasks created?)
Pre-EA | Initiate Project | Review project description (high Level) | Assumes that tombstone data has been entered by proponent during intake | EAO | Accept Draft Project Description |  |  | Pull in Text |  |  |  | Project Description | 10(1)b, 10(1)a
Pre-EA | Initiate Project | Determine appropriate Project Process - Section 10 | Selection would launch appropriate plan and buckets. *This plan assumes 10(1)c | EAO | Accept Draft Project Description | x |  | Pull in Text | Options |  |  | Intake Question Responses, Link to Intake content | 10(1)a, 10(1)b, 10(1)c, No EA Required
Pre-EA | Initiate Project | Generate Default Project Template based on above selection | This assumes S10.1c | System
Pre-EA | Set up Project Space | Review and Modify Activities in Plan | This assumes that the user is viewing this from the Task view | EAO | Project Space Initiated |  |  | No Action Requ'd
Pre-EA | Set up Project Space | Add Milestone Dates to the Plan |  | EAO | Project Space Initiated |  |  | Milestone Date Picker |  |  |  | Milestones
| Set up Project Space | Invite Proponent to Project Space |  | EAO | Project Space Initiated |  |  | Notification
Pre-EA | Set up Project Space | Create Project Team and Assign roles in System | Visibility / Stakeholder Management | EAO | Project Space Initiated |  |  | Contact Management / Stakeholder |  |  |  | Contact Management
Pre-EA | Set up Project Space | Review and populate Stakeholder Members in System | in Stakeholder management location | EAO | Project Space Initiated |  |  | Contact Management / Stakeholder |  |  |  | Contact Management
Pre-EA | Set up Project Space | Review and Modify Notification Matrix |  | EAO | Project Space Initiated | x per time |  | Link |  |  |  | Notification Matrix
Pre-EA | Populate Initial Project Content | Confirm and Modify Value Components created in system |  | P | None | EAO Confirm and Modify as required, content input by Proponent | [5 empty] | VC Artifacts
Pre-EA | Populate Initial Project Content | Populate Issue Tracking Table with known issues |  | P | None |  |  | Create Issue |  |  |  | Issue Artifacts
Pre-EA | Populate Initial Project Content | Populate FNI Tracking Table with known Interests |  | P | None |  |  | Create FNI |  |  |  | FNI Artifacts
Pre-EA | Populate Initial Project Content | EAO Confirm and Modify as required, content input by Proponent |  | EAO | None |  |  | Status |  |  |  | VC Artifacts
| Approve Project Description | INSERT DOCUMENT UPLOAD PROCESS |  |  | Project Description
| Approve Project Description | INSERT REVIEW-REVISE COMMENT WORKFLOW |  |  | Project Description
| Approve Project Description | INSERT APPROVAL WORKFLOW |  |  | Project Description
Pre-EA | Approve Project Description | Publish Project Description |  | EAO | Project Description |  |  | Visibility / Publish
Pre-EA | Issue Section 10(1)c | Create Draft Section 10 |  | EAO | Section 10.1.c |  |  | Generate Form |  |  |  | Section 10 Artifact
Pre-EA | Issue Section 10(1)c | INSERT REVIEW-REVISE COMMENT WORKFLOW |  |  | Section 10.1.c
Pre-EA | Issue Section 10(1)c | INSERT APPROVAL WORKFLOW |  |  | Section 10.1.c
Pre-EA | Issue Section 10(1)c | Notify Stakeholders of Section10(1)c |  | EAO | Section 10.1.c |  |  | Notification
Pre-EA | Issue Section 10(1)c | Publich 10(1)c |  | EAO | Section 10.1.c
Pre Application | Document Strength of Claim | Identify First Nations for Consultation | TFNCI | EAO | Strength of Claim |  |  | No Action Requ'd
Pre Application | Document Strength of Claim | Research First Nations Strength of Claim | TFNCI | EAO | Strength of Claim |  |  | No Action Requ'd
Pre Application | Document Strength of Claim | Set Consultation level | TFNCI | EAO | Strength of Claim | x |  | No Action Requ'd
Pre Application | Document Strength of Claim | Amend Stakeholder List | in Stakeholder management location | EAO | Strength of Claim |  |  | Contact Management |  |  |  | Stakeholder List
Pre Application | Input Project Content - for Section 11 | Add Description and Boundary information and documentation to each of the Value Components |  | P | Section 11 |  |  | Input VC Data | Status
Pre Application | Issue Section 11 Document | Create Draft S11 | Upload not mandatory at this step If completed earlier | EAO | Section 11 | Create Draft S11 |  | Generate Form |  |  | Complete if Document uploaded to S11 Deliverable Space | Section 11 Artifact
Pre Application | Issue Section 11 Document | Submit Draft Section 11 for First Nations' Comment |  | EAO | Section 11 | #VALUE! |  | Document Upload | Notification
Pre Application | Issue Section 11 Document | INSERT REVIEW-REVISE COMMENT WORKFLOW |  | FN, EAO | Section 11
Pre Application | Finalize and Approve Section 11 | Complete final revisions of Draft Section 11 |  | EAO | Section 11 | #REF! |  | Approve Workflow
Pre Application | Finalize and Approve Section 11 | Upload final Draft for approval |  | EAO | Section 11
Pre Application | Finalize and Approve Section 11 | INSERT APPROVAL PROCESS |  | EAO | Section 11
Pre Application | Finalize and Approve Section 11 | Issue Section 11 and notify Stakeholders |  | EAO | Section 11 |  |  | Notification | Visibility / Publish
Pre Application | Input Project Content - for AIR | Provide methodology and other supporting information/ documentation |  | P | Value Component Document |  |  | Input other Artifact Data | Status
Pre Application | Input Project Content - for AIR | Review Methodology entered by Proponent |  | EAO | Value Component Document |  |  | Status
Pre Application | Input Project Content - for AIR | Create Value Component Document |  | EAO | Value Component Document |  |  | Generate Form
Pre Application | Confirm Working Group Participation | Send request to desired Working Group Participants |  | EAO | Draft AIR |  |  | Notification
Pre Application | Confirm Working Group Participation | Confirm Participation |  | EAO | Draft AIR |  |  | Status
Pre Application | Confirm Working Group Participation | Update Stakeholder List with confirmed names |  | EAO | Draft AIR |  |  | Contact Management | Status
Pre Application | Confirm Working Group Participation | Ensure Working Group members are assigned to relevant Value Components | Ben - Not sure how to assign this | EAO | Draft AIR |  |  | Input VC Data
Pre Application | Input Project Content - DRAFT AIR | Add Description and Boundary information and documentation to each of the Value Components |  | P | Section 11 |  |  | Input VC Data | Status
Pre Application | Create Draft AIR | INSERT DOCUMENT UPLOAD PROCESS | Approve and Publish to wrap to end. |  | Draft AIR
Pre Application | Create Draft AIR | INSERT REVIEW-REVISE COMMENT WORKFLOW |  |  | Draft AIR
Pre Application | Create Draft AIR | INSERT APPROVAL WORKFLOW |  |  | Draft AIR
Pre Application | Create Draft AIR | Publish Draft AIR for Public and Stakeholders |  | EAO | Draft AIR |  |  | Visibility / Publish
Pre Application | Draft AIR Public Comment Period | Initiate Draft AIR Public Comment Period if Required |  | EAO | Draft AIR |  |  | Yes/No | Status |  | YES [INSERT PUBLIC COMMENT PERIOD WORKFLOW}, No [ TAKE NO ACTION]
Pre Application | Create AIR | INSERT DOCUMENT UPLOAD PROCESS | Approve and Publish to wrap to end. |  | AIR
Pre Application | Create AIR | INSERT REVIEW-REVISE COMMENT WORKFLOW |  |  | AIR
Pre Application | Create AIR | INSERT APPROVAL WORKFLOW |  |  | AIR
Pre Application | Create AIR | Finalize and Publish AIR to identified stakeholders |  | EAO | AIR |  |  | Visibility / Publish
Pre Application | Create Table of Concordance | INSERT DOCUMENT UPLOAD PROCESS |  | P | Draft Application
Pre Application | Submit Application | INSERT DOCUMENT UPLOAD PROCESS |  | P | Draft Application
Pre Application | Pre-Application Wrap-Up | Schedule Evaluation Period |  | EAO | Draft Application |  |  | Milestone Date Picker
Pre Application | Pre-Application Wrap-Up | Notify Working Group of upcoming Evaluation Period |  | EAO | Draft Application |  |  | Notification
Pre Application | Pre-Application Wrap-Up | Schedule Working Group Metings as required |  | EAO | Draft Application |  |  | Calendar
Evaluation | Initate Evaluation Period | Fomally Accept Application |  | EAO | Draft Application |  |  | Status | Notification
Evaluation | Initate Evaluation Period | Notify / Send Application, AIR, and Table of Concordance to Working Group Members |  | EAO | Draft Application |  |  | Notification
Evaluation | Initate Evaluation Period | Send Invoice to Proponent |  | EAO | Draft Application |  |  | Status |  |  | only for first time
Evaluation | Initate Evaluation Period | Confirm Working Group received Application, AIR, and Table of Concordance |  | EAO | Draft Application |  |  | Status
Evaluation | 30 Day Evaluation Period | Formally Initiate 30 Day Evaluation Period |  | EAO | Evaluation Decision |  |  | Milestone Date Picker | Status - Complete / Not Complete
Evaluation | 30 Day Evaluation Period | INSERT REVIEW-REVISE COMMENT WORKFLOW | Need to define scope of comment process / approval process |  | Evaluation Decision
| 30 Day Evaluation Period | INSERT APPROVAL WORKFLOW |  |  | Evaluation Decision
Evaluation | Evaluation Wrap-up | Schedule Application Decision Period |  | EAO | Application |  |  | Milestone Date Picker
Evaluation | Evaluation Wrap-up | Notify Working Group of upcoming Review Period |  | EAO | Application |  |  | Notification
Evaluation | Evaluation Wrap-up | Schedule Working Group Application Evaluation Meetings as required |  | EAO | Application |  |  | Calendar
Review | Initate Review Period | Notify / Send Application to Working Group Members |  | EAO | Application |  |  | Notification
Review | Initate Review Period | Confirm Working Group received Application Package of Materials |  | EAO | Application
Review | Initate Review Period | Formally Initiate 180 Day Review Period |  | EAO | Application |  |  | Milestone Date Picker | Status - Complete / Not Complete
Review | Initate Review Period | Alert Proponent/Stakeholders 180 Day Review commenced |  | System | Application |  |  | Alert
Review | Initate Review Period | Publish Application |  | EAO | Application |  |  | Visibility / Publish
Review | Application Review | INSERT REVIEW-REVISE COMMENT WORKFLOW |  |  | Application
Review | Public Comment Period | INSERT PUBLIC COMMENT PERIOD PROCESS |  |  | Application |  |  | Public Comment Period Workflow
Review | Approve Application | INSERT APPROVAL PROCESS |  |  | Application
Review | Review Wrap-Up | Write Assessment Document |  | EAO | Referral Package Sign-off |  |  | Document Upload
Review | Review Wrap-Up | Create Referral Package |  | EAO | Referral Package Sign-off |  |  | Associate Documents | Document Upload
Review | Review Wrap-Up | Schedule Ministerial Meetings for Decision Phase |  | EAO | Referral Package Sign-off |  |  | Calendar | Status
Review | Review Wrap-Up | Confirm Value Components, Issues, FNI, etc. are resolved |  | EAO | Referral Package Sign-off |  |  | Input other Artifact Data
Review | Review Wrap-Up | Review and Complete Conditions |  | EAO | Referral Package Sign-off |  |  | Conditions
Review | Review Wrap-Up | INSERT CONDITION APPROVAL PROCESS (TBD) |  | EAO | Referral Package Sign-off
Review | Review Wrap-Up | Revise and Finalize Certified Project Description |  | EAO/P | Referral Package Sign-off |  |  | Pull in Text | Status |  |  | Certified Project Description
Review | Review Wrap-Up | Confirm with Ministers that the Decision Phase is to proceed |  | EAO | Referral Package Sign-off |  |  | Status
Decision | Initiate Decision Period | Provide documents to Ministers, including Separate Submissions |  | EAO | Ministers' Decision |  |  | Alerts (System) | Notification
Decision | Initiate Decision Period | Associate Separate Submissions in the system |  | EAO | Ministers' Decision |  |  | Associate Documents
Decision | Minister Review - Approve Application | Initiate Approval Matrix |  | EAO | Ministers' Decision |  |  | Launch Button (Go) |  |  | Approval Matrix
Decision | Initiate Decision Period | Confirm Ministers have received package of materials |  | EAO | Ministers' Decision |  |  | Status
Decision | Initiate Decision Period | Formally initiate 45 Day Decision Period |  | EAO | Ministers' Decision |  |  | Launch Button (Go) |  |  | Start Tracking for this
Decision | Initiate Decision Period | Hold Ministerial Meetings / Briefings |  | EAO | Ministers' Decision |  |  | Status
Decision | Minister Review - Approve Application | Review Document and Provide Approval Recommendation |  | Approver | Ministers' Decision |  |  | Approval Rationale |  |  | Not Approved, More information needed , Approved
Decision | Not Approved | Document Approval Decision |  | EAO | Ministers' Decision |  |  | Options | Rationale |  | Not Approved, More information needed , Approved
Decision | Not Approved | Notify Stakeholders |  | EAO | Ministers' Decision |  |  | Notification
Decision | More information needed | Document Approval Decision |  | EAO | Ministers' Decision |  |  | Options | Rationale |  | Not Approved, More information needed , Approved
Decision | More information needed | Return Project to a previous Milestone? |  | EAO | Ministers' Decision |  |  | yes/no |  |  | YES: Launch 'RETURN TO PREVIOUS MILESTONE ACTIVITY', No: Notify Stakeholders
Decision | More information needed | Notify Stakeholders |  | EAO | Ministers' Decision |  |  | Notification
Decision | Approved | Document Approval Decision |  | EAO | Ministers' Decision |  |  | Options | Rationale |  | Not Approved, More information needed , Approved
Decision | Approved | Notify Stakeholders |  | EAO | Ministers' Decision |  |  | Notification
Decision | Create Certificate | Finalize Conditions |  | EAO | Certificate |  |  | Conditions
| Create Certificate | Finalize Draft Certified Project Description |  | EAO | Certificate
Decision | Create Certificate | Create Certificate |  | EAO | Certificate |  |  | Generate Form
Decision | Create Certificate | INSERT APPROVAL WORKFLOW |  | System | Certificate
Decision | Create Certificate | Adjust Project Dates |  | EAO | Certificate |  |  | Milestone Date Picker
Decision | Create Certificate | Publish Project Content |  | EAO | Certificate |  |  | Visibility / Publish
Decision | Create Certificate | Notify Stakeholders |  | EAO | Certificate
Decision | Complete Decision Phase | Close Phase |  | EAO | Certificate |  |  | Status |  |  | Close Phase
Post-Certification | Initiate Certificate Extension | Select to Initiate Certificate Extension |  | EAO | Certificate Extension |  | Certificate date - 9 months | Alerts (System) | Launch Button (Go) |  | INSERT CERTIFICATE EXTENSION ALERT EAO at 'Start Date'
Post-Certification | Initiate Substantially Started Process | Initiate Substantially Started Process |  | EAO / P | Substantially Started |  |  | Launch Button (Go) |  |  | INSERT SUBSTANTIALLY STARTED PROCESS

## Process Types
Process | Column1
Alerts (System)
Approval Workflow
Approved/Denied | toggle - associated to visibility
Approval Notes
Associate Documents | Separate Submissions
Associate VC and Issue Picker
Calendar / Schedule
Conditions | List?
Contact Management / Stakeholder
Create FNI
Create Issue | on comment,
Create VC
Input other Artifact Data
Input Issue Data
Input VC Data
Document Approval Workflow
Document Upload | Mandatory Tags and associated 'bucket'
Generate Form
Launch Button (Go)
Milestone Date Picker | List of Milestones with start and End Dates (Maybe it's just a collapse?? But should be full project view)
No Action Requ'd
Notification
Options | This would be a set of options for a given step. Click to select.
Public Comment Period Workflow
Public Comment Process
Pull Down
Pull in Text
Rationale | Text
Revision Notes
Revise Workflow
Status | Not Started, In Progress, Complete
Timeline Point in Time Picker | Return project plan to this point in the process
Text Entry
Yes/No
Visibility / Publish

## Public Comment Period Process
Phase | Activity | Task | Notes | Role (EAO / P) - Visibility | Milestone | Requirement / Dependencies | Start Date | End Date | Process | Process | Process | Logic | Metadata / Tags (Bucket association / Where does this information need to go) | Resulting Action (New Tasks created?)
| Public Comment Period | Determine Start and end period |  | EAO | Public Comment Period |  |  |  | Milestone Date Picker
| Public Comment Period | Define Information Package | May need to be able to select from existing documents | EAO | Public Comment Period |  |  |  | Document Upload
| Public Comment Period | Alert Proponent / Generate new tasks (below) |  | System | Public Comment Period
| Public Comment Period | Submit Advert for approval |  | P | Public Comment Period |  |  |  | Document Upload | Alerts
| Public Comment Period | INSERT APPROVAL PROCESS |  |  | Public Comment Period |  |  |  | Approve Workflow
| Public Comment Period | Post Advert. on [input date - start date -7 days] | INSERT INSTRUCTIONS | P | Public Comment Period |  |  | Due: Milestone Start - 7 | Approve Workflow | Status
| Public Comment Period | Provide Documentation on Advert Posting |  |  | Public Comment Period |  |  |  | Document Upload
| Public Comment Period | Provide Information Package for Comment Period |  | P / EAO (Exceptions) | Public Comment Period |  |  | Due: Milestone Start - 7 | Document Upload |  |  | This task P for D AIR, and Project Description. EAO for VC Document
| Public Comment Period | Review Information Package |  | EAO | Public Comment Period |  |  | Due: Milestone Start - 7 | No Action Requ'd
| Public Comment Period | Approve Information Package |  |  | Public Comment Period |  |  |  | Approved
| Public Comment Period | Publish Information to public site |  | EAO | Public Comment Period |  |  | Due: Milestone Start - 7 | Visibility / Publish
| Public Comment Period | Confirm 'go-no-go' open Public Comment Period |  | EAO | Public Comment Period |  |  | Due: Milestone Start | Status
| Public Comment Period | Open Comment Period |  | EAO | Public Comment Period |  |  | Due: Milestone Start | Visibility / Publish
| Public Comment Process | Initiate Comment Review |  | System | Public Comment Period |  |  |  | Public Comment Process
| Public Comment Process | Review and Redact comment for publishing to proponent and public |  | EAO | Public Comment Period |  |  |  | Pull in Text |  |  | Text is editable | Public Comment
| Public Comment Process | Approve |  | EAO | Public Comment Period |  |  |  | Approved | Visibility / Publish
| Public Comment Process | Categorize Public Comment |  | P | Public Comment Period |  |  |  | Associate VC and Issue Picker | Create VC | Create Issue |  |  | Generate Next Comment Set
| Public Comment Process | Add new Issue if Required |  | P | Public Comment Period
| Public Comment Process | Edit response if required |  | P | Public Comment Period |  |  |  | Input VC Data | Input Issue Data |  |  | Associated VC
| Public Comment Process | Confirm all comments responded to |  | EAO | Public Comment Period
| Public Comment Period | Confirm 'go-no-go' Close Public Comment Period |  | EAO | Public Comment Period |  |  |  | Milestone Date Picker
| Public Comment Period | Close Comment Period |  | EAO | Public Comment Period |  |  | End Date | Visibility / Publish
| Public Comment Period | Confirm Proponent has categorized and responded to all Comments |  | EAO | Public Comment Period
| Public Comment Period | Create Additional Issues as a result of Comments |  | P | Public Comment Period |  |  |  | Create Issue

## Document Upload (For Approval)
Phase | Activity | Task | Notes | Role (EAO / P) - Visibility | Milestone | Requirement / Dependencies | Start Date | Process | Process | Process | Logic | Metadata / Tags (Bucket association / Where does this information need to go) | Resulting Action (New Tasks created?)
| Document Upload | Upload Document(s) for Approval |  | P |  |  |  | Document Upload | Alerts (System) |  |  | Document Upload
| Document Upload | Associate Document |  | P |  |  |  | Document Upload |  |  |  | Tag
| Document Upload | Confirm Receipt of Document |  | EAO |  |  |  | Notification |  |  |  | Notification
| Document Upload | Verify content is available and appropriate |  | EAO |  |  |  | Status |  |  |  | Visibility / Publish

## Review-Revise Comment Workflow
Phase | Activity | Task | Notes | Role (EAO / P) - Visibility | Milestone | Requirement / Dependencies | Start Date | Process | Process | Process | Logic | Metadata / Tags (Bucket association / Where does this information need to go) | Resulting Action (New Tasks created?)
| Commenting: Review and Revise Document | Ensure Reviewers are entered into the system |  | EAO
| Commenting: Review and Revise Document | Provide materials to reviewers |  | EAO
| Commenting: Review and Revise Document | Review Materials Provided |  | Various |  |  |  | Link |  |  |  | Associated Notification / Process Milestone |  |  | Associated milestone document
| Commenting: Review and Revise Document | Comment |  | Various |  |  |  | Comment |  |  |  |  | Tag | Tags for locations within the document?? | Associated milestone document
| Commenting: Review and Revise Document | Review and Redact comment |  | EAO |  |  |  | Comment |  |  |  |  | Visibility / Publish | edit comment
| Commenting: Review and Revise Document | Associate Comment |  | P |  |  |  | Associate VC and Issue Picker
| Commenting: Review and Revise Document | Revise Value Components, Issues, Etc as required |  | P |  |  |  | Input other Artifact Data | Revision Notes |  |  |  | Input VC Data
| Commenting: Review and Revise Document | Alert Working Group Members |  | System |  |  |  | Alert
| Commenting: Review and Revise Document | Review Comments to determine if any further action is required |  | EAO |  |  |  | Options | Rationale |  | Revision Required, Resolved |  | If Revise, Return to beginning
|  | RE-INSERT REVIEW-REVISE COMMENT WORKFLOW (CYCLICAL) |  | System
| Finalize Comment Period | Determine next steps |  | EAO |  |  |  | Options |  |  | Create Condition
| Finalize Comment Period | Create Condition |  | EAO |  |  |  | Conditions
| Finalize Comment Period | Change status for Value Component to Resolved (if appropriate) |  | EAO |  |  |  | Input VC Data
| Finalize Comment Period | Change Status for Issue to Resolved (if appropriate) |  | EAO |  |  |  | Input Issue Data
| Finalize Comment Period | Close Comment Period |  | EAO |  |  |  | Status |  |  |  |  | Remove comment ability

## Approval Workflow
Phase | Activity | Task | Notes | Role (EAO / P) - Visibility | Milestone | Requirement / Dependencies | Start Date | Process | Process | Process | Logic | Metadata / Tags (Bucket association / Where does this information need to go) | Resulting Action (New Tasks created?)
| Approve [Document] | Confirm Receipt |  | EAO |  |  |  | Notification
| Approve [Document] | Initiate Approval Matrix |  | EAO |  |  |  | Launch Button (Go) |  |  | Approval Matrix
| Approve [Document] | Alert 1st Approver |  | System |  |  |  | Alert
| Approve [Document] | Review Document and Provide Approval Recommendation |  | Approver |  |  |  | Approval Rationale |  |  | Not Approved, Approved with Revisions , Approved
| Approve [Document] | Alert Next Approver | [8 empty] | REPEAT UNTIL ALL APPROVERS DONE
| Not Approved | Document Approval Decision |  | EAO |  |  |  | Options | Rationale |  | Not Approved, Approved with Revisions , Approved
| Not Approved | Return Project to a previous Milestone? |  | EAO |  |  |  | yes/no |  |  | YES: Launch 'RETURN TO PREVIOUS MILESTONE ACTIVITY', No: Notify Stakeholders
| Approved with Revisions | Document Approval Decision |  | EAO |  |  |  | Options | Rationale |  | Not Approved, Approved with Revisions , Approved
| Approved with Revisions | Revise Document |  | P |  |  |  | Document Upload |  | Revision Notes
| Approved | Document Approval Decision |  | EAO |  |  |  | Options | Rationale |  | Not Approved, Approved with Revisions , Approved

## Substantially Started
Phase | Activity | Task | Notes | Role (EAO / P) - Visibility | Milestone | Requirement / Dependencies | Start Date | End Date | Process | Process | Process | Logic | Metadata / Tags (Bucket association / Where does this information need to go) | Resulting Action (New Tasks created?)
Post-Certification | Initiate Substantially Started Process | Initiate Substantially Started Process |  | EAO/P | Substantially Started |  |  |  | Launch Button (Go)
Post-Certification | Initiate Substantially Started Process | Complete and submit Substantially Started Request Form |  | P | Substantially Started |  |  |  | Generate Form
Post-Certification | Initiate Substantially Started Process | Select Reviewers |  | EAO | Substantially Started |  |  |  | Contact Management / Stakeholder
Post-Certification | Initiate Substantially Started Process | INSERT COMMENT WORKFLOW |  |  | Substantially Started
Post-Certification | Initiate Substantially Started Process | Research and Verify Substantially Started Claim |  | C and E | Substantially Started
Post-Certification | Initiate Substantially Started Process | INSERT COMMENT WORKFLOW |  |  | Substantially Started
Post-Certification | Initiate Substantially Started Process | Revise and Finalize Substantially Started Document |  | P | Substantially Started
Post-Certification | Initiate Substantially Started Process | Conclude Comment Period |  | EAO | Substantially Started | [5 empty] | COMMENTS No Longer Available
Post-Certification | Initiate Substantially Started Process | Write Recommendation |  | EAO / C and E | Substantially Started
Post-Certification | Initiate Substantially Started Process | Prepare Substantially Started Package |  | EAO / C and E | Substantially Started
Post-Certification | Initiate Substantially Started Process | Ensure Approver selected in the system |  | EAO | Substantially Started |  |  |  | Contact Management / Stakeholder
Post-Certification | Initiate Substantially Started Process | Confirm Approver availability |  |  | Substantially Started
Post-Certification | Initiate Substantially Started Process | Make Documents visible to Approver |  |  | Substantially Started
Post-Certification | Approval Process | INSERT APPROVAL PROCESS |  |  | Substantially Started
Post-Certification | Initiate Project Close-Out | INSERT CLOSE OUT PROCESS (TBD) |  |  | Substantially Started

## Return to a previous Milestone
Phase | Activity | Task | Notes | Role (EAO / P) - Visibility | Milestone | Requirement / Dependencies | Start Date | Process | Process | Process | Logic | Metadata / Tags (Bucket association / Where does this information need to go) | Resulting Action (New Tasks created?)
| Return to Previous Milestone | Select Milestone from Pick list |  | EAO |  |  |  | Timeline Point in Time Picker
| Return to Previous Milestone | Adjust Milestone Dates |  | EAO |  |  |  | Milestone Date Picker
| Return to Previous Milestone | Notify Proponent and Stakeholders |  | EAO |  |  |  | Notification
| Return to Previous Milestone | Archive Documents |  | System
| Return to Previous Milestone | Re-launch Plan |  | System |  |  |  | Alerts (System)

## Certificate Extension
Phase | Activity | Task | Notes | Role (EAO / P) - Visibility | Milestone | Requirement / Dependencies | Start Date | Process | Process | Process | Logic | Metadata / Tags (Bucket association / Where does this information need to go) | Resulting Action (New Tasks created?)
Post-Certification | Certificate Extension Process | Notify Stakeholders |  | EAO | Certificate Extension |  |  | Notification
Post-Certification | Certificate Extension Process | Record Decision for extension |  | P | Certificate Extension |  |  | Options | Rationale |  | No Extension (Project Closed) [6.2.1], Extend, Initiate Substantially Started Process
Post-Certification | Certificate Extension Process | Complete Extension Request Form |  | P | Certificate Extension |  |  | Generate Form | Document Upload
Post-Certification | Certificate Extension Process | Determine if First Nations' Consultation is Required |  | EAO | Certificate Extension |  |  | Yes/No |  |  | Yes [6.2.1], No [6.3.1]
Post-Certification | Certificate Extension Process | Make Extension Request Visible |  | EAO | Certificate Extension |  |  | Visibility / Publish
Post-Certification | Certificate Extension Process | Notify First Nations' for consultation |  | EAO | Certificate Extension |  |  | Notification
Post-Certification | Comment Period | INSERT COMMENT WORKFLOW |  |  | Certificate Extension
Post-Certification | Certificate Extension Process | Confirm Approver availability |  | Eao | Certificate Extension |  |  | Status
Post-Certification | Certificate Extension Process | Make Extension Request and other documents visible to Approver |  | EAO | Certificate Extension |  |  | Visibility / Publish
Post-Certification | Certificate Extension Process | Ensure Approver selected in the system |  | EAO | Certificate Extension |  |  | Status
Post-Certification | Approval Process | INSERT APPROVAL PROCESS |  |  | Certificate Extension
Post-Certification | Certificate Extension Process | Document Approval Decision and Rationale |  | EAO | Certificate Extension |  |  | Options | Rationale |  | Extension Approved , Extension Denied
Post-Certification | Certificate Extension Process | Notify Stakeholders |  | EAO | Certificate Extension |  |  | Notification
Post-Certification | Certificate Extension Process | Extend Project Date |  | EAO | Certificate Extension |  |  | Milestone Date Picker
Post-Certification | Certificate Extension Process | Publish Extension materials and revised date |  | EAO | Certificate Extension |  |  | Visibility / Publish
Post-Certification | Initiate Project Close-out | INSERT CLOSE OUT PROCESS (TBD) |  |  | Certificate Extension

## Section 13
Generate Document Template | EAO | Template
Fill out S13 Document | EAO
Upload, Review, Comment, Approve | Stakeholders | Approval Process

## Pages
Homepage | Project Info, Spatial Documents, tabs to artifacts | Outside Project Space
Notification Matrix | Stakeholder by Deliverable | User Log-in Screen-set
Process Artifacts (S10, 11, AIR) |  | Proponent Project(s) 'Management' Screen-set | Dashboard(ian)
Value Components/Issues/FNI/Etc - Bucket |  | Proponent Intake Screen-set | Intake questions - could be questionnaire style
Proponent BI Screen-set
Public BI Screen-set
EAO BI Screen-set
EAO Admin Screen-set
Project Search Screen-set
|  | Certificate/Condition Library | Standard ized List
Inside Project Space
|  | Project Determination Screen-set | Is this part of the Intake Screen Set
|  | Project Tombstone | This should have all the Proponent information entered at intake
|  | Notification Matrix Screen-set | by deliverable (potentially milestone)
|  | Contact Management Screen-set (incl. set roles) | Stakeholder Management - role: will this connect with notification matrix?
Artifact Visibility Screen-set
|  | Deliverables - screen sets | Added by Lena - following our meeting
|  | First Nations Interests (FNI) Screen-Set | Added by Lena - following our meeting
|  | Issues - Screen Sets | Added by Lena - following our meeting
|  | File Upload Screen-set | Document Management
|  | Project 'Management' Screen-set | Tasks?
Task/Vital Stats Screen-set (the 'main hub')
Issue Tracking Screen-set
Commenting Screen-set (Incl. tagging)
|  | F.N. Consultation Screen-set (SoC, tracking etc.) | Can we discuss so that we can build appropriate processes
Publish Project Information Screen-set (RSS, Email, Website)
Project 'Calendar' Management Screen-set
|  | Bucket' Data Entry/Management Screen-set | ??
PCP/Open House setup Screen-set (incl. polling)
|  | Approval Screen-set | Please identify what this does - LS
|  | Condition Creation | Added by Lena
|  | Approval Process Flow | Added by Lena
|  | Comment Process Flow | Added by Lena

## Assumptions
Tasks Not completed in one phase will carry forward for visibility in another phase
Document Approval Process to have minor variation for each Deliverable

## Commonly added Task Groups
Public Comment Period
Section 13
Issue Creation/Modification
VC Creation / Modification
FNI Creation/ Modification
Open House

## Sheet4
Working Group Meetings | Milestone(ian)
Ability to schedule tasks with associated alerts - ie. Return thing/response

## VC Modification Process
Phase | Activity | Task | Subtask | Standard Process | Notes | Role (EAO / P) - Visibility | Milestone | Requirement / Dependencies | Start Date | Process | Process | Process | Logic | Metadata / Tags (Bucket association / Where does this information need to go) | Resulting Action (New Tasks created?)
| Create and Modify Value Components | Create or select existing Value Components as Required |  |  |  | P |  |  |  | Create VC | Pull Down |  | Pull in list of existing VCs
|  | Add Description |  |  |  | P |  |  |  | Input VC Data |  |  | Make Text Editable | VC Description
|  | Add or Modify Response |  |  |  | P |  |  |  | Input VC Data |  |  | Make Text Editable | VC Response
|  | Upload Spatial Study Area Boundary Documents |  |  |  | P |  |  |  | Document Upload
|  | Upload Study Data |  |  |  | P |  |  |  | Document Upload

## Issue Process
Phase | Activity | Task | Notes | Role (EAO / P) - Visibility | Milestone | Requirement / Dependencies | Start Date | Process | Process | Process | Logic | Metadata / Tags (Bucket association / Where does this information need to go) | Resulting Action (New Tasks created?)
| Create New Issue | Create New Issue |  | P | [6 empty] | Create Issue
| Create New Issue | Write Description |  | p |  |  |  |  | Create New Issue |  | Input Issue Data |  |  | Created Issue, Description
| Create New Issue | Write Response |  | p |  |  |  |  | Create New Issue |  | Input Issue Data | Document Upload |  | Created Issue, Response
| Create New Issue | Create New Value Component if Required |  | p | [6 empty] | Create VC |  |  | Created Issue, VC
| Create New Issue | Associate Issue to Existing Value Component |  | P | [6 empty] | Associate VC and Issue Picker

## Public Comment Process
Phase | Activity | Task | Subtask | Standard Process | Notes | Role (EAO / P) - Visibility | Milestone | Requirement / Dependencies | Start Date | End Date | Process | Process | Process | Logic | Metadata / Tags (Bucket association / Where does this information need to go) | Resulting Action (New Tasks created?)
| Public Comment Process | Review and Redact comment for publishing to proponent and public |  |  |  | EAO |  |  |  |  | Pull in Text |  |  | Text is editable | Public Comment
|  | Approve |  |  |  | EAO |  |  |  |  | Approved | Visibility / Publish
|  | Categorize Public Comment |  |  |  | P |  |  |  |  | Associate VC and Issue Picker | Create VC | Create Issue |  |  | Generate Next Comment Set
|  | Edit response if required | [8 empty] | Input VC Data | Input Issue Data |  |  | Associated VC
Confirm

## Deliverable Review and Approval
Phase | Activity | Task | Standard Process | Notes | Role (EAO / P) - Visibility | Deliverable | Requirement / Dependencies | Type | Type | Type | Completion Rule | Metadata / Tags (Bucket association / Where does this information need to go) | Resulting Action (New Tasks created?)
| Input | Upload or Enter content |  |  | P | Variable |  | Document Upload | Status |  |  |  | System notification to EAO upon Completion
|  | Comfirm Receipt (Status = In Progress) |  |  | EAO |  | Upload or Enter content | Status |  |  | When status Complete, system to make visible to?? |  | System Notification to Proponent of in progress status
|  | Verify Content (status = Complete) |  |  | EAO
|  | Publish / Make Visible |  |  | EAO | [7 empty] | System publish/ change visibility
| Revise | Accept document for Revision
Schedule Working Group
Approve
Publish